## How to use
Greenfield Test Execution Tracker
What this is | The execution log for the greenfield test cycle. The test cases themselves live in docs/qa/suites/ as Markdown — this workbook records what happened when you ran them.
Sheets | Test Cases — one row per case, filter by Owner to find yours. ¦ Defects — every failure you raise. ¦ Daily Log — one row per tester per day. ¦ Summary — live counts, no typing needed.
Every session
1. | Run the environment health check from GREENFIELD_TEST_PLAN.md §2 and record it on the Daily Log.
2. | Filter Test Cases by your initial in the Owner column and work in TC-ID order within a suite.
3. | Open the matching suite file in docs/qa/suites/ for the full steps — this sheet holds titles only.
4. | Set Status for EVERY case you touch. Leaving it 'Not Run' means nobody looked, which is the one thing the tracker must never be ambiguous about.
5. | On a failure: screenshot first, then add a row on Defects, then put the DEFECT-ID in the case row.
6. | Blocked is not Fail. If a case cannot run because an earlier one failed, mark it Blocked and name the blocking DEFECT-ID — otherwise one root cause shows up as ten failures.
7. | End of session: fill in the Daily Log and post the same one-liner in the team channel.
Re-testing | When a defect is fixed, re-run the original case and fill the Re-test columns. A defect is closed by a passing test case, not by a developer's say-so.
Editing cases | Never change a case's steps here. Edit the Markdown in docs/qa/suites/, then re-run 'python docs/qa/build_tracker.py' — your logged results are preserved by TC-ID.
Cycle size | 253 test cases · Tester A: 62 · Tester B: 81 · Tester C: 110
Out of scope | The brownfield track. Do not create a Brownfield project.

## Test Cases
TC-ID | Suite | Title | Type | Priority | Screen | Persona | Automation | Owner | Status | Run date | Tester | Actual result / notes | Defect ID | Re-test | Re-test date
TC-001 | TS-01 | Create a workspace and land on the setup checklist | E2E | Critical | /signup → /setup | P1 Owner-Admin | Yes | A | Not Run
TC-002 | TS-01 | Signup rejects an email that already has an account | Negative | High | /signup | P1 Owner-Admin | Yes | A | Not Run
TC-003 | TS-01 | Signup rejects a password under 8 characters | Negative | High | /signup | Any | Yes | A | Not Run
TC-004 | TS-01 | Signup with a blank workspace name | Negative | Medium | /signup | Any | Yes | A | Not Run
TC-005 | TS-01 | Signup rejects a malformed email address | Negative | Medium | /signup | Any | Yes | A | Not Run
TC-006 | TS-01 | The password strength meter responds as you type | UX | Low | /signup | Any | No | A | Not Run
TC-007 | TS-01 | Signup shows a submitting state while the workspace is created | UX | Medium | /signup | Any | No | A | Not Run
TC-008 | TS-01 | Log in with valid credentials | Functional | Critical | /login | P1 Owner-Admin | Yes | A | Not Run
TC-009 | TS-01 | Log in with the wrong password | Negative | High | /login | P1 Owner-Admin | Yes | A | Not Run
TC-010 | TS-01 | Log in with an email that has no account | Negative | Medium | /login | Any | Yes | A | Not Run
TC-011 | TS-01 | Repeated failed logins lock the account | Negative | High | /login | P1 Owner-Admin | Yes | A | Not Run
TC-012 | TS-01 | Login shows a submitting state | UX | Low | /login | P1 Owner-Admin | No | A | Not Run
TC-013 | TS-01 | Login returns you to the page you originally asked for | Functional | High | /login → /work-items | P1 Owner-Admin | Yes | A | Not Run
TC-014 | TS-01 | Sign out from the avatar menu | Functional | High | app shell → /login | P1 Owner-Admin | Yes | A | Not Run
TC-015 | TS-01 | An anonymous visitor cannot reach a protected route | Permission | Critical | /work-items → /login | Any | Yes | A | Not Run
TC-016 | TS-01 | A signed-in user visiting /login is sent to the dashboard | Functional | Medium | /login → / | P1 Owner-Admin | Yes | A | Not Run
TC-017 | TS-01 | Request a password reset | Functional | High | /reset | P1 Owner-Admin | Yes | A | Not Run
TC-018 | TS-01 | Set a new password from a reset link and log in with it | E2E | High | /reset?token=… → /login | P1 Owner-Admin | No | A | Not Run
TC-019 | TS-01 | An invalid or expired reset link shows the invalid state | Negative | Medium | /reset?token=… | Any | Yes | A | Not Run
TC-020 | TS-01 | The reset form is prefilled with a hardcoded sample address | UX | Medium | /reset | Any | Yes | A | Not Run
TC-021 | TS-01 | Join a workspace from an invitation link | E2E | Critical | /accept-invite?token=… → / | P10 Engineer | No | A | Not Run
TC-022 | TS-01 | An expired or already-used invite link shows the expired state | Negative | Medium | /accept-invite?token=… | Any | Yes | A | Not Run
TC-501 | TS-01 | Signup with a blank full name is refused silently | Negative | Medium | /signup | Any | Yes | A | Not Run
TC-502 | TS-01 | A short password on the invitation form is refused silently | Negative | Medium | /accept-invite?token=… | P10 Engineer | No | A | Not Run
TC-503 | TS-01 | A signed-in user opening an invite or reset link is bounced with no explanation | UX | Medium | /accept-invite?token=… · /reset?token=… → / | P1 Owner-Admin | Yes | A | Not Run
TC-504 | TS-01 | A short password on the reset form is refused silently | Negative | Medium | /reset?token=… | P1 Owner-Admin | No | A | Not Run
TC-023 | TS-02 | The users table lists everyone in the workspace | Functional | High | /admin/users | P1 Owner-Admin | Yes | A | Not Run
TC-024 | TS-02 | Invite a teammate with a project and role grant | Functional | Critical | /admin/users | P1 Owner-Admin | Yes | A | Not Run
TC-025 | TS-02 | Inviting an address that is already a member is refused | Negative | High | /admin/users | P1 Owner-Admin | Yes | A | Not Run
TC-026 | TS-02 | Resend a pending invitation | Functional | Medium | /admin/users | P1 Owner-Admin | No | A | Not Run
TC-027 | TS-02 | Revoke a pending invitation | Functional | High | /admin/users | P1 Owner-Admin | No | A | Not Run
TC-028 | TS-02 | The users empty state | UX | Low | /admin/users | P1 Owner-Admin | No | A | Not Run
TC-029 | TS-02 | The role matrix renders with a column per role | Functional | High | /admin/roles | P1 Owner-Admin | Yes | A | Not Run
TC-030 | TS-02 | Toggling a role grants it and updates gate-role coverage | Functional | Critical | /admin/roles | P1 Owner-Admin | Yes | A | Not Run
TC-031 | TS-02 | The last admin cannot remove their own admin role | Negative | Critical | /admin/roles | P1 Owner-Admin | Yes | A | Not Run
TC-033 | TS-02 | The project select on the roles screen is inert | UX | Low | /admin/roles | P1 Owner-Admin | Yes | A | Not Run
TC-034 | TS-02 | A non-admin deep-linking to /admin/users is refused | Permission | Critical | /admin/users | P10 Engineer | Yes | A | Not Run
TC-035 | TS-02 | Admin navigation is hidden from a non-admin | Permission | High | app shell (sidebar) | P10 Engineer | Yes | A | Not Run
TC-036 | TS-02 | A non-admin on /test-reporting gets the workspace-admin refusal | Permission | Medium | /test-reporting | P10 Engineer | Yes | A | Not Run
TC-521 | TS-02 | A user with two roles on one project sees that project twice in the selector | Functional | Medium | /admin/roles → app shell top bar | P10 Engineer | Yes | A | Not Run
TC-522 | TS-02 | An unknown /admin/* URL renders a developer placeholder | Negative | Low | /admin/<anything> | P1 Owner-Admin | Yes | A | Not Run
TC-037 | TS-03 | Create a greenfield project | Functional | Critical | /projects/new → /profile | P1 Owner-Admin | Yes | A | Not Run
TC-038 | TS-03 | A duplicate project name is accepted, creating two identical projects | Negative | High | /projects/new → /profile | P1 Owner-Admin | Yes | A | Not Run
TC-039 | TS-03 | The Track control explains itself via a tooltip | UX | Low | /projects/new | P1 Owner-Admin | No | A | Not Run
TC-040 | TS-03 | Brownfield routes to onboarding | Functional | Medium | /projects/new → /onboarding | P1 Owner-Admin | Yes | A | Not Run
TC-041 | TS-03 | Save the project profile and return to the setup checklist | E2E | Critical | /profile?setup=1 → /setup | P1 Owner-Admin | Yes | A | Not Run
TC-042 | TS-03 | Re-saving the profile creates a new version | Functional | High | /profile | P1 Owner-Admin | Yes | A | Not Run
TC-043 | TS-03 | The profile will not save without a description, and says nothing about it | Negative | High | /profile | P1 Owner-Admin | Yes | A | Not Run
TC-044 | TS-03 | Export policy offers a row per exportable phase | Functional | Medium | /profile | P1 Owner-Admin | Yes | A | Not Run
TC-045 | TS-03 | UX Design export is locked to internal | UX | Low | /profile | P1 Owner-Admin | Yes | A | Not Run
TC-046 | TS-03 | The repositories empty state | UX | Medium | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-047 | TS-03 | Add a repository | Functional | Critical | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-048 | TS-03 | Adding the same repository twice is refused | Negative | High | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-049 | TS-03 | Set and save a repository's preview URL | Functional | Medium | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-050 | TS-03 | The topology chip changes once a second repository exists | Functional | Medium | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-051 | TS-03 | The Set default button is unwired | Functional | Medium | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-052 | TS-03 | Remove a repository | Functional | Medium | /repositories | P1 Owner-Admin | Yes | A | Not Run
TC-053 | TS-03 | Only a tech lead or admin can register a repository | Permission | Critical | /repositories | P10 Engineer / P5 Tech Lead | No | A | Not Run
TC-054 | TS-03 | The setup checklist reflects completed steps | Functional | High | /setup | P1 Owner-Admin | Yes | A | Not Run
TC-055 | TS-03 | Setup step 4 never completes, however many integrations you connect | UX | Medium | /setup → /integrations → /setup | P1 Owner-Admin | No | A | Not Run
TC-541 | TS-03 | A plain engineer can create a project | Permission | High | /projects/new | P10 Engineer | Yes | A | Not Run
TC-542 | TS-03 | A plain engineer can rewrite the project profile every agent reads | Permission | Critical | /profile | P10 Engineer | Yes | A | Not Run
TC-056 | TS-04 | The capability grid renders all six capability cards in order | UX | High | /integrations | P1 Owner-Admin | Yes | B | Not Run
TC-057 | TS-04 | Choosing a vendor reveals that vendor's binding and secret fields | Functional | High | /integrations/:capability | P1 Owner-Admin | Yes | B | Not Run
TC-058 | TS-04 | Connect the Documentation store capability (happy path) | Functional | Critical | /integrations/docstore | P1 Owner-Admin | No | B | Not Run
TC-059 | TS-04 | A stored secret is never echoed back to the browser | Functional | Critical | /integrations/docstore | P1 Owner-Admin | Yes | B | Not Run
TC-060 | TS-04 | Saving without retyping the secret does not erase it | Negative | High | /integrations/docstore | P1 Owner-Admin | No | B | Not Run
TC-061 | TS-04 | Test connection reports success for valid credentials | Functional | High | /integrations/docstore | P1 Owner-Admin | No | B | Not Run
TC-062 | TS-04 | Test connection reports the reason and a fix hint for a bad credential | Negative | High | /integrations/docstore | P1 Owner-Admin | No | B | Not Run
TC-063 | TS-04 | A failed connection turns the card badge to Failed and the link to Fix connection | UX | High | /integrations | P1 Owner-Admin | No | B | Not Run
TC-064 | TS-04 | Code intelligence is built in, connected, and needs no credential | Functional | Medium | /integrations/codeintel | P1 Owner-Admin | Yes | B | Not Run
TC-065 | TS-04 | A vendor with no live check reports OK even for junk credentials | Negative | Medium | /integrations/testmgmt | P1 Owner-Admin | No | B | Not Run
TC-066 | TS-04 | Re-saving an already-connected capability updates it in place, never duplicating it | Negative | High | /integrations/docstore | P1 Owner-Admin | No | B | Not Run
TC-067 | TS-04 | A non-admin cannot use Integrations | Permission | High | /integrations, /integrations/docstore | P10 Engineer | No | B | Not Run
TC-068 | TS-04 | The Couldn’t save banner uses a curly apostrophe where the rest of the app uses a straight one | UX | Low | /integrations/:capability | P1 Owner-Admin | No | B | Not Run
TC-069 | TS-05 | The not-started state shows Step A and a greyed-out Step B | UX | High | /connect | P1 Owner-Admin | Yes | C | Not Run
TC-070 | TS-05 | Generating an enrollment token shows it exactly once | Functional | Critical | /connect | P1 Owner-Admin | No | C | Not Run
TC-071 | TS-05 | Step B reveals the two real commands to run | Functional | High | /connect | P1 Owner-Admin | No | C | Not Run
TC-072 | TS-05 | The companion connects and the screen flips to Connected | E2E | Critical | /connect | P1 Owner-Admin | No | C | Not Run
TC-073 | TS-05 | Both companion pills read Companion: Ready | UX | High | Any screen (app shell) | P1 Owner-Admin | Yes | C | Not Run
TC-074 | TS-05 | Stopping the companion turns the pills to Companion: Offline after the 2-minute window | Functional | High | Any screen (app shell) | P1 Owner-Admin | No | C | Not Run
TC-075 | TS-05 | The offline state on /connect explains how to restart and offers a new token | UX | Medium | /connect | P1 Owner-Admin | No | C | Not Run
TC-076 | TS-05 | Generate new token on the offline screen issues a working token | Functional | Medium | /connect | P1 Owner-Admin | No | C | Not Run
TC-077 | TS-05 | A failed token request silently shows a fake token and a success screen | Negative | Critical | /connect | P1 Owner-Admin | No | C | Not Run
TC-078 | TS-05 | Disconnect machine stops the running companion's token from authenticating | Functional | High | /connect | P1 Owner-Admin | No | C | Not Run
TC-581 | TS-05 | The Projects multi-select on the enrollment screen has no effect on the token issued | UX | Medium | /connect | P1 Owner-Admin | No | C | Not Run
TC-582 | TS-05 | A non-admin engineer can enrol a companion machine | Permission | High | /connect | P10 Engineer | No | C | Not Run
TC-079 | TS-06 | A project with no work items shows the empty state | UX | Medium | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-080 | TS-06 | Create an epic from the drawer (happy path) | Functional | Critical | /work-items | P1 Owner-Admin | No | B | Not Run
TC-081 | TS-06 | The create drawer will not submit without a title | Negative | High | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-082 | TS-06 | The board renders the full lifecycle as columns, in order | Functional | High | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-083 | TS-06 | A newly created work item lands in the first column as a draft | Functional | High | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-084 | TS-06 | The Board/List toggle switches views and the list shows the right columns | Functional | Medium | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-085 | TS-06 | The search box filters the board | Functional | Medium | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-086 | TS-06 | The Phase filter offers only phases items are actually in | Functional | Medium | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-087 | TS-06 | The level chips filter by work-item level | Functional | High | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-088 | TS-06 | The Tasks chip switches the board to the two build columns | Functional | High | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-089 | TS-06 | The Role filter offers only roles that own a phase an item is in | Functional | Medium | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-090 | TS-06 | The Status filter narrows the board by work-item state | Functional | Medium | /work-items | P1 Owner-Admin | Yes | B | Not Run
TC-091 | TS-06 | The epic detail screen shows the plan-tier lifecycle | Functional | High | /work-items/:id | P1 Owner-Admin | Yes | B | Not Run
TC-092 | TS-06 | The Test cases button on an epic opens its test-case screen | Functional | Medium | /work-items/:id | P1 Owner-Admin | Yes | B | Not Run
TC-093 | TS-06 | The task detail screen shows the build-tier lifecycle and its parent | Functional | High | /work-items/:id | P1 Owner-Admin | No | B | Not Run
TC-094 | TS-06 | The Repository card appears only on multi-repo projects | Negative | Medium | /work-items/:id | P1 Owner-Admin | No | B | Not Run
TC-095 | TS-06 | The defect detail screen shows the remediation lifecycle | Functional | High | /work-items/:id | P1 Owner-Admin | Yes | B | Not Run
TC-096 | TS-06 | The board reflects a work item that has moved through phases | E2E | High | /work-items, /work-items/:id | P1 Owner-Admin | No | B | Not Run
TC-601 | TS-06 | An unknown work-item id shows a not-found panel, not a broken epic screen | Negative | Medium | /work-items/:id | P1 Owner-Admin | Yes | B | Not Run
TC-602 | TS-06 | The Task Breakdown screen's greenfield default state | UX | Medium | /work-items/:id/breakdown | P1 Owner-Admin | No | B | Not Run
TC-603 | TS-06 | Re-triggering a phase on a task asks for confirmation first | Functional | High | /work-items/:id | P1 Owner-Admin | No | B | Not Run
TC-604 | TS-06 | A non-admin engineer can create work items | Permission | High | /work-items, /work-items/:id | P10 Engineer | No | B | Not Run
TC-097 | TS-07 | Trigger panel renders with the companion online | Functional | Critical | /runs | P1 Owner-Admin | No | C | Not Run
TC-098 | TS-07 | Each phase button names the role that will decide its gate | UX | Medium | /runs | P1 Owner-Admin | No | C | Not Run
TC-099 | TS-07 | The work-item picker is searchable and reports no matches | Functional | Medium | /runs | P1 Owner-Admin | No | C | Not Run
TC-100 | TS-07 | Triggering Ideation on the epic starts a run | Functional | Critical | /runs | P1 Owner-Admin | No | C | Not Run
TC-101 | TS-07 | The new run appears in the Runs table with the correct columns | Functional | High | /runs | P1 Owner-Admin | No | C | Not Run
TC-102 | TS-07 | The run console header identifies the run | Functional | High | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-103 | TS-07 | The run console walks the status sequence to Awaiting gate | E2E | Critical | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-104 | TS-07 | Log lines appear in the run console | Functional | High | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-105 | TS-07 | The work item moves off Not started once its phase runs | Functional | High | /work-items · /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-106 | TS-07 | Triggering a phase that is already running is blocked | Negative | Critical | /runs | P1 Owner-Admin | No | C | Not Run
TC-107 | TS-07 | The re-run modal can be cancelled without starting a run | Negative | High | /runs | P1 Owner-Admin | No | C | Not Run
TC-108 | TS-07 | Confirming a re-run creates a new run and keeps the old one | Functional | High | /runs | P1 Owner-Admin | No | C | Not Run
TC-109 | TS-07 | An offline companion blocks the trigger panel | Negative | Critical | /runs | P1 Owner-Admin | No | C | Not Run
TC-110 | TS-07 | A failed run shows the reason and offers a retry | UX | High | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-111 | TS-07 | The Runs table empty state | UX | Medium | /runs | P1 Owner-Admin | Yes | C | Not Run
TC-112 | TS-07 | A run id that does not exist shows Run not found | Negative | Medium | /runs/:id | P1 Owner-Admin | Yes | C | Not Run
TC-701 | TS-07 | Triggering a different phase while a run is live fails with a 409 banner | Negative | Critical | /runs | P1 Owner-Admin | No | C | Not Run
TC-702 | TS-07 | A parked run offers Resume from where it stopped | UX | High | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-703 | TS-07 | An auto-retried run links to its continuation run | UX | Medium | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-704 | TS-07 | Any project member can trigger a phase, whatever their role | Permission | High | /runs | P10 Engineer | No | C | Not Run
TC-705 | TS-07 | Any project member can take over a parked run | Permission | Medium | /recovery | P10 Engineer | No | C | Not Run
TC-113 | TS-08 | A paused run shows Needs answer in the console | Functional | Critical | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-114 | TS-08 | The sidebar Clarifications count increments | UX | Medium | any screen (app shell) | P1 Owner-Admin | No | C | Not Run
TC-115 | TS-08 | The question renders on /clarifications under its tier | Functional | Critical | /clarifications | P1 Owner-Admin | No | C | Not Run
TC-116 | TS-08 | Answering the question resumes the same run | E2E | Critical | /clarifications · /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-117 | TS-08 | Each question kind renders the right input | UX | High | /clarifications | P1 Owner-Admin | No | C | Not Run
TC-118 | TS-08 | A blank required question blocks submission | Negative | High | /clarifications | P1 Owner-Admin | No | C | Not Run
TC-119 | TS-08 | Accept all suggestions & inferences fills the Tier 2/3 answers | Functional | Medium | /clarifications | P1 Owner-Admin | No | C | Not Run
TC-120 | TS-08 | The answered confirmation names the work item and says the run resumed | UX | Medium | /clarifications | P1 Owner-Admin | No | C | Not Run
TC-121 | TS-08 | A user with no membership on the project cannot answer | Permission | High | /clarifications | Any (a non-member account) | No | C | Not Run
TC-122 | TS-08 | The Clarifications empty state | UX | Low | /clarifications | P1 Owner-Admin | Yes | C | Not Run
TC-801 | TS-08 | With two questions outstanding, only the first is on screen | Functional | High | /clarifications | P1 Owner-Admin | No | C | Not Run
TC-123 | TS-09 | A completed run opens a gate and surfaces it everywhere | Functional | Critical | /runs/:id · /gates · / (dashboard) | P1 Owner-Admin | No | C | Not Run
TC-124 | TS-09 | The Gates empty state | UX | Medium | /gates | P1 Owner-Admin | Yes | C | Not Run
TC-125 | TS-09 | The pending approvals table columns | UX | High | /gates | P1 Owner-Admin | No | C | Not Run
TC-126 | TS-09 | The decision card renders for the role holder | Functional | Critical | /gates | P2 Product Owner | No | C | Not Run
TC-127 | TS-09 | Approving with a comment resumes the run to completion | E2E | Critical | /gates · /runs/:id | P2 Product Owner | No | C | Not Run
TC-128 | TS-09 | The artifact stops being a draft only once its gate is approved | Functional | Critical | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-129 | TS-09 | Wrong role gets a read-only card — PRD gate (Product Owner) | Permission | Critical | /gates | P10 Engineer | No | C | Not Run
TC-130 | TS-09 | Wrong role gets a read-only card — Architecture gate (Architect) | Permission | Critical | /gates | P2 Product Owner | No | C | Not Run
TC-131 | TS-09 | A tenant admin can decide any gate | Permission | High | /gates | P1 Owner-Admin | No | C | Not Run
TC-132 | TS-09 | A project admin is shown the read-only card for another role's gate | Permission | High | /gates | Any (a project-admin account that is not a tenant admin) | No | C | Not Run
TC-133 | TS-09 | Rejecting a gate with a comment fails the run | Functional | Critical | /gates · /runs/:id | P2 Product Owner | No | C | Not Run
TC-134 | TS-09 | After a rejection the work item is still workable and re-triggering makes a new run | E2E | Critical | /runs · /work-items | P1 Owner-Admin | No | C | Not Run
TC-135 | TS-09 | An already-decided gate cannot be decided again | Negative | High | /gates | P2 Product Owner | No | C | Not Run
TC-136 | TS-09 | The Decided history tab | UX | Medium | /gates | P2 Product Owner | No | C | Not Run
TC-137 | TS-09 | The UX Design gate blocks approval until all 22 WCAG 2.2 criteria are ticked | Functional | Critical | /gates | P4 Designer | No | C | Not Run
TC-138 | TS-09 | The standalone criteria-gate screen | UX | Low | /gates/:id/criteria | P1 Owner-Admin | Yes | C | Not Run
TC-139 | TS-09 | The Testing gate carries two platform-derived conditions | Negative | High | /gates | P7 QA Lead | No | C | Not Run
TC-140 | TS-09 | The Deployment gate carries 7 readiness criteria | Functional | High | /gates | P9 DevOps | No | C | Not Run
TC-901 | TS-09 | The Task Breakdown gate reviews every task's repository assignment | Functional | Critical | /gates | P1 Owner-Admin | No | C | Not Run
TC-902 | TS-09 | The work-item screen offers a second Approve/Reject with no role check | Permission | Critical | /work-items/:id | P10 Engineer | No | C | Not Run
TC-903 | TS-09 | The merge gate requires the Tech Lead role (08 Code Review) | Permission | High | /gates | P10 Engineer · P5 Tech Lead | No | C | Not Run
TC-904 | TS-09 | Rejecting the UX Design criteria gate is never blocked by unticked criteria | Negative | High | /gates | P4 Designer | No | C | Not Run
TC-905 | TS-09 | Rejecting a build-tier merge gate stops the merge and leaves the PR open | Functional | Critical | /gates · /runs/:id · /work-items/:id | P5 Tech Lead | No | C | Not Run
TC-141 | TS-10 | Registry lists an artifact after a phase run, with the right columns | Functional | Critical | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-142 | TS-10 | Only Draft and Published status badges are reachable — Pending gate never renders | UX | Medium | /artifacts · /gates | P1 Owner-Admin | No | C | Not Run
TC-143 | TS-10 | Phase, Type and Status filters and the search box narrow the registry | Functional | Medium | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-144 | TS-10 | Filtered-empty state appears when nothing matches | UX | Medium | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-145 | TS-10 | Truly-empty registry on a project that has never run a phase | UX | Medium | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-146 | TS-10 | Export appears only once a phase's gate has been approved | Functional | High | /gates → /artifacts | P1 Owner-Admin | No | C | Not Run
TC-147 | TS-10 | Preview opens read-only with the never-an-editor banner and version history | Functional | High | /artifacts/:id | P1 Owner-Admin | No | C | Not Run
TC-148 | TS-10 | A markdown artifact previews as formatted markdown, not raw source | UX | Medium | /artifacts/:id | P1 Owner-Admin | No | C | Not Run
TC-149 | TS-10 | A listed artifact with no readable body shows Artifact not found | UX | Medium | /artifacts/:id | P1 Owner-Admin | No | C | Not Run
TC-150 | TS-10 | An unknown artifact id shows Artifact not found | Negative | Medium | /artifacts/:id | P1 Owner-Admin | Yes | C | Not Run
TC-151 | TS-10 | A draft or staged artifact cannot be published — the gate rule holds | Negative | Critical | /artifacts/:id/publish | P1 Owner-Admin | No | C | Not Run
TC-152 | TS-10 | An internal re-publish of a gate-approved artifact succeeds and changes nothing | Functional | Critical | /artifacts/:id/publish | P1 Owner-Admin | No | C | Not Run
TC-153 | TS-10 | Target capability select and the Destination field's per-vendor help text | Functional | High | /artifacts/:id/publish | P1 Owner-Admin | No | C | Not Run
TC-154 | TS-10 | A phase with an internal-only export policy offers no external target | UX | Medium | /artifacts/:id/publish | P1 Owner-Admin | No | C | Not Run
TC-155 | TS-10 | UX Design artifacts are hard-locked to internal with the Figma note | UX | Medium | /artifacts/:id/publish | P1 Owner-Admin / P4 Designer | No | C | Not Run
TC-156 | TS-10 | An external publish with no connector fails loudly and never claims a push | Negative | High | /integrations · /artifacts/:id/publish | P1 Owner-Admin | No | C | Not Run
TC-241 | TS-10 | A failed registry request renders as an empty registry, not as an error | UX | High | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-242 | TS-10 | A multi-state wireframe artifact previews behind a state switcher | Functional | Medium | /artifacts/:id | P1 Owner-Admin | No | C | Not Run
TC-243 | TS-10 | An artifact owned by an external system of record shows the read-there card | Functional | Medium | /artifacts/:id | P1 Owner-Admin | No | C | Not Run
TC-244 | TS-10 | The registry has no pagination and no sortable columns | UX | Low | /artifacts | P1 Owner-Admin | No | C | Not Run
TC-157 | TS-11 | The lineage graph renders nodes and edges once artifacts exist | Functional | High | /traceability | P1 Owner-Admin | No | B | Not Run
TC-158 | TS-11 | The legend's third entry is unreachable — only Published and Draft colour any node | UX | Medium | /traceability | P1 Owner-Admin | No | B | Not Run
TC-159 | TS-11 | Clicking a node opens the artifact preview, or the external URL | Functional | High | /traceability → /artifacts/:id | P1 Owner-Admin | No | B | Not Run
TC-160 | TS-11 | A graph node can be reached and activated from the keyboard | UX | Medium | /traceability | P1 Owner-Admin | No | B | Not Run
TC-161 | TS-11 | The graph shows the empty state on a project with no artifacts | UX | Medium | /traceability | P1 Owner-Admin | No | B | Not Run
TC-162 | TS-11 | The graph shows a loading state before the lineage arrives | UX | Low | /traceability | P1 Owner-Admin | No | B | Not Run
TC-163 | TS-11 | The live traceability screen has no phase/type/highlight filters and no zoom buttons | UX | Medium | /traceability | P1 Owner-Admin | No | B | Not Run
TC-164 | TS-11 | /transcripts lists only completed and approved runs, with the right columns | Functional | High | /transcripts | P1 Owner-Admin | No | B | Not Run
TC-165 | TS-11 | Opening a transcript shows the read-only replay with the provenance banner | Functional | High | /transcripts/:id | P1 Owner-Admin | No | B | Not Run
TC-166 | TS-11 | A run with no captured turns, and an unknown run id, both degrade gracefully | Negative | Medium | /transcripts/:id | P1 Owner-Admin | No | B | Not Run
TC-251 | TS-11 | A failed lineage request renders No lineage yet, not an error | UX | High | /traceability | P1 Owner-Admin | No | B | Not Run
TC-252 | TS-11 | A failed runs request renders No transcripts yet, not an error | UX | Medium | /transcripts | P1 Owner-Admin | No | B | Not Run
TC-167 | TS-12 | Every sidebar item navigates to its route and takes the active highlight | Functional | High | All (app shell) | P1 Owner-Admin | No | B | Not Run
TC-168 | TS-12 | The Gates, Clarifications and bell badges match the project's open counts | Functional | Medium | All (app shell) · /gates · /clarifications | P1 Owner-Admin | No | B | Not Run
TC-169 | TS-12 | A non-admin sees neither Test Reporting nor the Admin group | Permission | High | All (app shell) · /admin/users · /test-reporting | P10 Engineer | No | B | Not Run
TC-170 | TS-12 | The top-bar project select switches project and the screens re-scope | Functional | High | All (app shell) · / · /work-items · /artifacts | P1 Owner-Admin | No | B | Not Run
TC-171 | TS-12 | The avatar menu shows name and email, and Sign out works | Functional | High | All (app shell) → /login | P1 Owner-Admin | No | B | Not Run
TC-172 | TS-12 | The account menu closes on Escape and on an outside click | UX | Medium | All (app shell) | P1 Owner-Admin | No | B | Not Run
TC-173 | TS-12 | The companion pill appears in both the sidebar footer and the top bar | UX | Low | All (app shell) | P1 Owner-Admin | No | B | Not Run
TC-174 | TS-12 | The dashboard greeting changes when something needs you | UX | High | / | P1 Owner-Admin | No | B | Not Run
TC-175 | TS-12 | The three tiles and the Needs me rows, and their actions, navigate correctly | Functional | High | / → /gates · /clarifications · /runs/:id | P1 Owner-Admin | No | B | Not Run
TC-176 | TS-12 | The calm dashboard: all caught up, health rows, and nothing published | UX | Medium | / | P1 Owner-Admin | No | B | Not Run
TC-177 | TS-12 | With no project selected the dashboard shows the Get started panel | UX | Medium | / | P1 Owner-Admin | No | B | Not Run
TC-178 | TS-12 | An unknown URL redirects to / — there is no 404 page | UX | Medium | any unknown route → / | P1 Owner-Admin | Yes | B | Not Run
TC-179 | TS-12 | The tenant switcher and the notification bell are inert | UX | Low | All (app shell) | P1 Owner-Admin | No | B | Not Run
TC-180 | TS-12 | /dev/components is reachable without logging in and is linked from nowhere | Permission | Low | /dev/components | Any | No | B | Not Run
TC-261 | TS-12 | A failed dashboard request renders a calm, all-zero dashboard | UX | High | / | P1 Owner-Admin | No | B | Not Run
TC-262 | TS-12 | Onboarding is hidden on greenfield, and the screen behind it is still brownfield-only | UX | Medium | /onboarding | P1 Owner-Admin | No | B | Not Run
TC-263 | TS-12 | The project selector lists one option per role grant, so a two-role user sees duplicates | UX | Medium | All (app shell) | P1 Owner-Admin | No | B | Not Run
TC-264 | TS-12 | An unknown /admin/* route falls through to a developer placeholder | Negative | Medium | /admin/:anything | P1 Owner-Admin | Yes | B | Not Run
TC-265 | TS-12 | The Admin access needed panel also guards /test-reporting, and its copy does not say so | Permission | Medium | /test-reporting · /admin/users · /admin/roles | P10 Engineer | No | B | Not Run
TC-181 | TS-13 | The Test cases button on an epic opens the story's test-case screen | Functional | High | /work-items/:id, /work-items/:id/test-cases | P1 Owner-Admin | Yes | B | Not Run
TC-182 | TS-13 | Empty state on a story with no test cases | UX | Medium | /work-items/:id/test-cases | P1 Owner-Admin | Yes | B | Not Run
TC-183 | TS-13 | Add a test case by hand and see it in the table | Functional | High | /work-items/:id/test-cases | P1 Owner-Admin | Yes | B | Not Run
TC-184 | TS-13 | Add test case is blocked with an empty Title | Negative | Medium | /work-items/:id/test-cases | P1 Owner-Admin | Yes | B | Not Run
TC-185 | TS-13 | A failing create shows Couldn't add the test case. | Negative | Medium | /work-items/:id/test-cases | P1 Owner-Admin | No | B | Not Run
TC-186 | TS-13 | Automation badges, row actions and the N of M automated counter | UX | High | /work-items/:id/test-cases | P1 Owner-Admin | No | B | Not Run
TC-187 | TS-13 | Generate script triggers a Test Automation run for that test case | Functional | High | /work-items/:id/test-cases, /runs | P1 Owner-Admin | No | B | Not Run
TC-188 | TS-13 | /test-reporting is admin-only | Permission | High | /test-reporting | P10 Engineer | Yes | B | Not Run
TC-189 | TS-13 | No-project guard on /test-reporting | Negative | Medium | /test-reporting | P1 Owner-Admin | Yes | B | Not Run
TC-190 | TS-13 | No tokens yet empty state | UX | Medium | /test-reporting | P1 Owner-Admin | Yes | B | Not Run
TC-191 | TS-13 | Issue a CI token — shown once, with the copy-now warning and the CI snippet | Functional | Critical | /test-reporting | P1 Owner-Admin | No | B | Not Run
TC-192 | TS-13 | Revoke a token through the Revoke token? modal | Functional | High | /test-reporting | P1 Owner-Admin | No | B | Not Run
TC-213 | TS-13 | 09b Test Automation runs end-to-end — build PR and QA Lead merge gate | E2E | Critical | /work-items/:id/test-cases, /runs/:id, /gates, /artifacts | P1 Owner-Admin, P7 QA Lead | No | B | Not Run
TC-214 | TS-13 | CI posts a JUnit report — Last used flips and failing tests open defects | E2E | Critical | /test-reporting, /work-items | P1 Owner-Admin | No | B | Not Run
TC-215 | TS-13 | A revoked CI token is rejected and does not update Last used | Negative | Critical | /test-reporting | P1 Owner-Admin | No | B | Not Run
TC-193 | TS-14 | Stopping the companion mid-run parks the run for takeover | Functional | Critical | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-194 | TS-14 | /recovery renders the parked run | UX | High | /recovery | P1 Owner-Admin | No | C | Not Run
TC-195 | TS-14 | Reconnect & re-run starts a fresh run and leaves the parked one in history | Functional | Critical | /recovery, /runs/:id, /runs | P1 Owner-Admin | No | C | Not Run
TC-196 | TS-14 | Take over manually ends the parked run | Functional | High | /recovery, /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-197 | TS-14 | Resume from where it stopped continues a run paused on an error | Functional | High | /runs/:id | P5 Tech Lead | No | C | Not Run
TC-198 | TS-14 | A report-timeout park offers no resume action | Negative | High | /runs/:id | P1 Owner-Admin | No | C | Not Run
TC-199 | TS-14 | A parked run can be re-triggered where a live run cannot | Functional | High | /runs | P1 Owner-Admin | No | C | Not Run
TC-200 | TS-14 | /recovery empty state when nothing is parked | UX | Medium | /recovery | P1 Owner-Admin | Yes | C | Not Run
TC-216 | TS-14 | A late report reconciles the same parked run, with no button pressed | Functional | Critical | /runs/:id, /gates, /artifacts | P1 Owner-Admin | No | C | Not Run
TC-217 | TS-14 | Triggering a different phase while a run is live fails with a red banner, not a modal | Negative | High | /runs | P1 Owner-Admin | No | C | Not Run
TC-201 | TS-15 | Zero to ready — signup to a dashboard that says you can start | E2E | Critical | /signup, /setup, /projects/new, /profile, /repositories, /connect, / | P1 Owner-Admin | No | C | Not Run
TC-202 | TS-15 | Invite the team until every gate role is covered | E2E | Critical | /admin/users, /accept-invite, /admin/roles | P1 Owner-Admin | No | C | Not Run
TC-203 | TS-15 | Plan tier, part 1 — Ideation from trigger to approved artifact | E2E | Critical | /work-items, /runs, /runs/:id, /clarifications, /gates, /artifacts | P1 Owner-Admin, P2 Product Owner | No | C | Not Run
TC-204 | TS-15 | Plan tier, part 2 — Requirements then PRD, each through its gate | E2E | Critical | /runs, /runs/:id, /gates, /artifacts, /work-items/:id | P1 Owner-Admin, P2 Product Owner | No | C | Not Run
TC-205 | TS-15 | Architecture — the Product Owner cannot decide it, the Architect can | E2E | Critical | /runs, /gates, /artifacts | P1 Owner-Admin, P2 Product Owner, P3 Architect | No | C | Not Run
TC-206 | TS-15 | UX Design — the criteria gate needs all 22 WCAG 2.2 criteria ticked | E2E | Critical | /runs, /gates, /gates/:id/criteria, /artifacts | P1 Owner-Admin, P4 Designer | No | C | Not Run
TC-207 | TS-15 | Task Breakdown — approve as Tech Lead and see the fan-out | E2E | Critical | /runs, /gates, /work-items, /work-items/:id/breakdown | P1 Owner-Admin, P5 Tech Lead | No | C | Not Run
TC-208 | TS-15 | Build tier — Implementation on a child task through its gate | E2E | Critical | /work-items/:id, /runs, /runs/:id, /gates | P1 Owner-Admin, P5 Tech Lead | No | C | Not Run
TC-209 | TS-15 | Testing — QA Lead approval produces test_case work items and artifacts | E2E | High | /runs, /gates, /artifacts, /work-items/:id/test-cases | P1 Owner-Admin, P7 QA Lead | No | C | Not Run
TC-210 | TS-15 | Security, CI/CD and Deployment — each to its own role | E2E | Critical | /runs, /gates, /gates/:id/criteria, /artifacts | P1 Owner-Admin, P8 Security Engineer, P9 DevOps | No | C | Not Run
TC-211 | TS-15 | The gate rule holds at the publish screen, and the chain agrees across surfaces | E2E | Critical | /artifacts, /artifacts/:id, /artifacts/:id/publish, /, /traceability | P1 Owner-Admin | No | C | Not Run
TC-212 | TS-15 | Rejection and recovery — reject a gate, re-trigger, pass on the second attempt | E2E | High | /gates, /runs, /runs/:id, /artifacts | P1 Owner-Admin, P2 Product Owner | No | C | Not Run
TC-218 | TS-15 | Code Review (08) leaves its evidence inside the build loop | E2E | High | /runs/:id, /artifacts, /work-items | P1 Owner-Admin | No | C | Not Run

## Defects
Defect ID | Title | Severity | Status | Found in TC | Screen / route | Steps to reproduce | Expected | Actual (verbatim) | Evidence (screenshot path) | Raised by | Raised on | Assigned to | Fix ref / commit | Re-tested by | Closed on

## Daily Log
Date | Tester | Hours | Env health OK? | Suites worked | Cases run | Pass | Fail | Blocked | What got in the way

## Summary
Cycle Summary
Everything below is calculated. Do not type in this sheet.
Overall
Total cases
Not Run
Pass
Fail
Blocked
Skipped
Executed (not 'Not Run')
By owner
Owner | Total | Pass | Fail | Blocked | Not Run
Tester A
Tester B
Tester C
By suite
Suite | Total | Pass | Fail | Blocked | Not Run | % done
TS-01
TS-02
TS-03
TS-04
TS-05
TS-06
TS-07
TS-08
TS-09
TS-10
TS-11
TS-12
TS-13
TS-14
TS-15
By priority
Priority | Total | Executed | Fail
Critical
High
Medium
Low
Defects
Critical — open
High — open
Medium — open
Low — open
Total raised
Exit criteria
All Critical priority cases executed
All High priority cases executed
90% of all cases executed
Zero open Critical defects
Zero open High defects